# Sprint #6 (3/19 – 3/26)

Scrum Master: Palwasha Newell

# Project

ETSU Marketplace is a university-only online marketplace that allows verified students to buy, sell, and exchange items and housing opportunities securely. It is a marketplace for students and only students to use. Built in ASP.NET MVC and C#.

# Sprint Goal

The goal for Sprint is to expand core marketplace functionality and improve usability by enhancing navigation, user profiles, messaging, and listing features while also improving code maintainability.

# PBIs Chosen

Numbers before PBI denote the story points for each item

Documents to upload:

- 18. Fix routing with back buttons

  - Chosen to provide control by allowing users to navigate through states without losing data.

- 14. Refactor code for Services/Controllers to be more DRY.

  - Chosen to improve readability and structure.

User Stories:

- 3. As a user, I want to scroll thru a listing’s images

  - Chosen because we wanted the users to be able to see the items for sale through images and not just the descriptions.

- 4. As a user, I want to view a seller’s profile to see their other listings.

  - Chosen so that the buyer can go to one seller instead of multiple sellers to buy items they want.

- 3. As a user, I want to add a username and bio to my profile.

  - Chosen so other users can learn more about the seller.

- 1. As a user, I want listings to support multiple categories.

  - Chosen so that items can be classified more accurately.

- 6. As a user, I want to be able to see messages for an item.

  - Chosen because it helps with communication between buyers and sellers.

- 7. As a user, I want to be able to choose items as my favorite.

  - Chosen so that the buyer can look at it later.

- 2. As a user, I would like to mark a listing as sold.

  - Chosen so that other buyers know what items or leases are still available and what is not.

# Sprint Planning Summary

The team met to plan Sprint 6 with a renewed focus on feature development after the documentation-heavy Sprint 5. We prioritized user experience improvements and backend refinements that would make the application more functional and scalable.

We selected PBIs that focused on navigation, communication, and profile enhancements, as these are essential for a marketplace environment. Additionally, we included refactoring tasks to ensure our codebase remains maintainable as the application grows.

Task ownership was distributed based on familiarity with features and previous work, allowing for efficient development.

# Tasks Planned

Documents to upload:

- Fix routing with back buttons (Jacob)

  - This task involved ensuring that navigation between pages preserves state and does not result in data loss. Jacob worked on adjusting routing logic and browser navigation handling.

  - Challenges: Managing state persistence across navigation.

  - Lessons Learned: Importance of user-friendly navigation and state management.

  - Planned time: 1 hour; Actual time: 1.5 hours

- Refactor Services/Controllers to be DRY (Jacob)

  - This task focused on eliminating redundant logic and improving code organization.

  - Challenges: Identifying duplicate logic without breaking functionality.

  - Lessons Learned: Clean architecture significantly improves scalability and readability.

  - Planned time: 2 hours; Actual time: 2 hours.

User Stories:

- Scroll through listing images (Jacob)

  - Implemented image carousel functionality for listings.

  - Challenges: Integrating UI components with existing image upload logic.

  - Lessons Learned: UI enhancements require coordination with backend data structures.

  - Planned time: 2 hours; Actual time: 2 hours

- View seller profile (Jacob)

  - Created profile pages displaying seller info and their listings.

  - Challenges: Linking listings dynamically to user profiles.

  - Lessons Learned: Reinforced understanding of relational data in MVC.

  - Planned time: 2 hours; Actual time: 2.5 hours

- Add username and bio (Jacob)

  - Extended user model and updated UI forms.

  - Challenges: Ensuring backward compatibility with existing accounts.

  - Lessons Learned: Small profile features greatly enhance user engagement.

  - Planned time: 1 hour; Actual time: 1 hour

- Support multiple categories (Jabari)

  - Modified listing structure to allow multiple categories.

  - Challenges: Updating database relationships and filters.

  - Lessons Learned: Schema changes impact multiple layers of the application.

  - Planned time: 3 hours; Actual time: 3 hours

- View messages for an item (Palwasha & Nathanael)

  - Implemented messaging visibility tied to listings.

  - Challenges: Integrating messaging with listing context.

  - Lessons Learned: Communication features are complex but critical for marketplaces.

  - Planned time: 3 hours; Actual time: 3.5 hours

- Favorite items (Palwasha)

  - Added ability to mark and store favorite listings.

  - Challenges: Persisting user-specific preferences.

  - Lessons Learned: Personalization features improve usability.

  - Planned time: 1.5 hours; Actual time: 1.5 hours

- Mark listing as sold (Palwasha)

  - Added status update functionality for listings.

  - Challenges: Ensuring sold items are reflected across UI and search.

  - Lessons Learned: Status management is important for accurate data representation.

  - Planned time: 1 hour; Actual time: 1 hour

# Roadblocks

No major roadblocks occurred during Sprint 6. Minor challenges involved integrating new features with existing logic, particularly with messaging and category updates.

# Sprint Review

## Sprint Goal

We successfully achieved our sprint goal by implementing multiple user-facing features and improving backend code structure.

## Acceptance testing by Product Owner

## Palwasha reviewed all implemented features, ensuring:

## Navigation works correctly

## Profiles display accurate information

## Messaging and favorites function properly

## Listings reflect updated statuses

## All features were accepted.

## Adjustments planned (Product)

## Future improvements include:

## Enhancing messaging with real-time updates

## Improving UI/UX consistency across new features

## Continuing backend optimization

## Revised Definition of Done (DoD)

## No major revisions were made. The Definition of Done continues to include:

- Fully functional feature implementation

- Integration with existing systems

- Code reviewed and tested

## Sprint review summary

Sprint 6 marked a return to feature-driven development.  The team successfully enhanced the usability and functionality of ETSU Marketplace by introducing key marketplace features such as messaging, favorites, and improved profiles.  The codebase was also improved through refactoring efforts.

# Sprint Retrospective

The team agreed that Sprint 6 was productive and well-balanced between frontend and backend work.  Communication improved compared to previous sprints, and task ownership was clear.

Areas for improvement:

- Continue refining task breakdown in Trello

- Improve documentation of feature-specific tasks

- Plan integration testing earlier in the sprint

## Velocity

Sprint 6 focused on story-point completion:

- Total story points completed: ~ 51

- PBIs completed: 9

- Average velocity per member: ~ 12-13 points

Estimated total development time: ~ 15-18 hours

# Backlog Grooming Summary

- Requirement Decomposition: Broke down user experience improvements into manageable PBIs.

- Point Estimation: Assigned points based on complexity and integration effort.

- Backlog Updates: Continued prioritization of user-centric features.

- Definition of Ready: Tasks were clearly defined with acceptance criteria before development.

# Summary of Daily Scrums

## Scrum 1 (Virtual) Updates:

- Jacob: Working on routing fixes and image scrolling feature.

- Jabari: Beginning multi-category support for listings.

- Palwasha: Planning favorites and sold status features.

- Nathanael: Continuing messaging system improvements.

.

## Scrum 2 Updates:

- Jacob: Completed profile features and refactoring tasks.

- Jabari: Finished Category implementation and testing.

- Palwasha: Completed favorites and sold functionality.

- Nathanael: Messaging integration nearing completion.

# GitHub Repository

https://github.com/sullinsje/ETSU-Marketplace

# Attendance

|  | 3/5 | 3/9 | 3/12 |
| --- | --- | --- | --- |
| Palwasha | Yes | Yes | Yes |
| Nathanael | No | Yes | Yes |
| Jabari | No | Yes | Yes |
| Jacob | No | Yes | Yes |

* Everyone but Palwasha was sick on 3/5

# Trello